## MOM points-18.09.21
S.N | Activity | Responsibility | Comments
2 | Project Management Time Plan/VELO GANTT chart modification required as below:
2.2 | Activity owners comments &Attachment file column to be add into VELO gantt chart. | Probity Technologies
2.3 | "Dependent activity column" to be add into VELO gantt chart. | Probity Technologies
2.4 | VELO gantt chart to be plotted "Month&Weekwise" instead of Day wise. | Probity Technologies
2.5 | In VELO gantt chart "activity Owners name" to be appear instead of "Department name". | Probity Technologies
2.6 | VELO gantt chart Header should include data such as,Project Leader,Hodek Part number,Customer Part number,Customer Name,RFQ/DER Number,Project Number,Customer Milestones(Customer Protosample Qty &Date,Customer PPAP Qty &Date,Customer SOP Date), Annual Volume Data(Next 5yrs),Engine details,Engine application details. | Probity Technologies | Provision int New Project
3 | ESCALATION:
3.2 | Escalation Mail to Top management after 2-3 reminder mail of Delayed activity to concern owner. | Probity Technologies